## Cover
This document outlines the Test Cases recommended by BT to test inter-operability with Customer's equipment.
| BT Details | Customer's Details
Company Name | British Telecom
Primary Technical Testing Contact Name | Naveen Kumar
Building | B26
Location / Sub-Building | Gemini
Street Number | Adastral Park
Post Town | Ipswich, UK
Post Code | IP5 3RE
Telephone | +441473641677
Email | naveen.s.kumar@bt.com
Note: CP is an abbreviation for Communication Provider, which also referred to as Customer

## Summary
Customer Name
TNOR Reference
Customer CPE
Start Date
Finish Date
Test Reference # | Area | IPX | Direction | Result
SDIN_IOT_CPBIBO_TC01 | Basic | Yes | CP -> BT
SDIN_IOT_CPBIBO_TC02 | Basic | Yes | BT -> CP
SDIN_IOT_CPBIBO_TC03 | Cancel | Yes | BT -> CP
SDIN_IOT_CPBIBO_TC04 | Cancel | Yes | CP -> BT
SDIN_IOT_CPBIBO_TC05 | Codec | Yes | BT -> CP
SDIN_IOT_CPBIBO_TC06 | Announcements | Yes | CP -> BT
SDIN_IOT_CPBIBO_TC07 | Refresh | Yes | CP -> BT
SDIN_IOT_CPBIBO_TC08 | Refresh | Yes | BT -> CP
SDIN_IOT_CPBIBO_TC09 | DTMF | Yes | CP -> BT
SDIN_IOT_CPBIBO_TC10 | DTMF | Yes | CP -> BT
SDIN_IOT_CPBIBO_TC11 | DTMF | Yes | CP -> BT
SDIN_IOT_CPBIBO_TC12 | DTMF | Yes | BT -> CP
SDIN_IOT_CPBIBO_TC13 | Hold | Yes | CP -> BT
SDIN_IOT_CPBIBO_TC14 | Hold | Yes | CP -> BT
SDIN_IOT_CPBIBO_TC15 | Short Code | Yes | CP -> BT
SDIN_IOT_CPBIBO_TC16 | Emergency | Yes | CP -> BT
SDIN_IOT_CPBIBO_TC17 | Emergency | Yes | CP -> BT
SDIN_IOT_CPBIBO_TC18 | Emergency | Yes | CP -> BT
SDIN_IOT_CPBIBO_TC19 | SDP | Yes | BT -> CP
SDIN_IOT_CPBIBO_TC20 | SDP | Yes | CP -> BT
SDIN_IOT_CPBIBO_TC21 | 503 | Yes | CP -> BT
SDIN_IOT_CPBIBO_TC22 | 404 | Yes | CP -> BT
SDIN_IOT_CPBIBO_TC23 | 486 | Yes | CP -> BT
SDIN_IOT_CPBIBO_TC24 | 403 | Yes | CP -> BT
SDIN_IOT_CPBIBO_TC25 | Anonymous | Yes | CP -> BT

## Proposed Tests
Test Case ID | Media Y/N | IPX | Area | Test Description | Expected Test Case Result | Result | Date | Tested By | Comments
SDIN_IOT_CPBIBO_TC01 | N | Yes | Basic | Test Description Initial connectivity tests to ensure SDIN IOT can start (CP -> BT) 1) OPTIONS message is sent from SDIN to CP: Check for the response message for OPTIONS from the CP's end. 2) Check for 'OPTIONS' message from CP to SDIN and verify whether CP is getting 200OK response message for OPTIONS from SDIN. 3) On net call; Basic call should be successfully established. Make a basic call from CP to SDIN. 4) PSTN Break-out; Basic call should be successfully established. Make a call from CP to PSTN. For test case 3) ensure you test all codecs supported by the CP, these will mean making a test call per codec supported. +441583427245 - SDIN test line +442076201687 – PSTN line | 1) Check SIP Options are going out of the S3 towards CP's platform. CP to check they receive option pings from BT. 2)CP / Customer Platform check they send 200 OK SIP response to the OPTION Message. Tester to verify 200ok is received. 3) CP to confirm whether they send option pings toward SDIN and if they are verify whether they are is getting 200OK response message from the SDIN platform. Tester to check BT side. 4) Verify that there are no private IP addresses in any part of SIP signalling and SDP messages. Ensure CP is using the correct signalling format chosen for both break-in and break-out calls. 5) Verify that the call gets connected successfully to two way audio. 6) CP to ensure that Request Uri , To, Contact and From must be in +E164 format and in SIP-URI format only. CP to check that they send a max-forwards of at least 50 in the SIP message. CP to ensure they send a PAID header in +E164 format and in SIP-URI format. ( Note SDIN does not handle RPID and P-Preferred-ID ). CP must send "user=phone" in the TO, FROM, PAID and request URI, wherever a SIP URI is present. CP to refer to Ofcom N1035, section 6.1 and 6.2. 6) Verify the SIP 3 way handshake is as expected. 7) Check what is offered by CP in the "supported" header. If CP offers "pre-condition", codec profiling needs to be enabled. 8) If "supported" header contacts "100rel", terminate the call on SNOM to verify PRACK exchange and call flow signalling is correct. 9) Note down any extra unrecognised headers in the comment section for discussion with the design team. 10) Check all mandatory SDP parameters are available. Check if media IP differs from signalling IP. 11) Make a note of any extra codecs CP has sent in the SDP that are not recorded in the CRF. 12) Verify that SDP does not contains "alternate" parameter and any other unrecognised attributes. Note these down for discussion with design. 13) Verify that CP sends "ptime" parameter as per their CRF selection. If not present, the CP needs to be informed that inter-working functionality might not work as expected on BT side. 14) Call to the PSTN should be forward and backward released. Verify, no non-standard behaviour on CP side.
SDIN_IOT_CPBIBO_TC02 | N | Yes | Basic | Test Description - Initial connectivity tests to ensure SDIN IOT can start (BT -> CP) 1) On net call; Basic call should be successfully established. Make a basic call from SDIN to CP. Ensure you test all codecs supported by CP, this will mean a test call per codec. Test 1) Ensure you test all codecs supported by the CP, BT tester to change their offer using soft-phone. | 1) Verify that there are no private IP addresses in any part of SIP signalling and SDP messages. Ensure CP is using the correct signalling format chosen in the CRF for both break-in and break-out calls. 2) Verify that the call gets connected successfully. Verify that Request Uri , To, Contact and From must be in +E164 format and in SIP-URI format only. Check that the max-forwards is at least 50 in the SIP message. Ensure that CP MUST send a PAID header in +E164 format and in SIP-URI format. ( Note SDIN does not handle RPID and P-Preferred-ID ). 3) Verify the SIP 3 way handshake is as expected. 4) Check what is offered by CP in the "supported" header. If CP offers "pre-condition", codec profiling needs to be enabled. 5) If "supported" header contacts "100rel", terminate the call on SNOM to verify PRACK exchange and call flow signalling is correct. 6) Note down any extra unrecognised headers in the comment section for discussion with the design team. 7) Verify that the call gets connected successfully and verify that the Media path is successful. 8) Check all mandatory SDP parameters are available. Check if media IP differs from signalling IP. 9) Make a note of any extra codecs CP has sent in the SDP that are not recorded in the CRF. 10) Verify that SDP does not contains "alternate" parameter and any other unrecognised attributes. Note these down for discussion with design. 11) Verify that CP sends "ptime" parameter as per their CRF selection. If not present, the CP needs to be informed that inter-working functionality might not work as expected on BT side. 12) Use the checks from 4 to 14 for all the connectivity calls. 13) Call to the PSTN should be forward and backward released. Verify, no non-standard behaviour on CP side.
SDIN_IOT_CPBIBO_TC03 | N | Yes | Cancel | Test Description CANCEL A call is made from SDIN to CP and the call is cancelled by SDIN before the call is answered by CP. Verify if CP is sending 487 "request terminated" on the reception of CANCEL by SDIN. Execute this test case with preferred codec of the CP. | The CANCEL method sent by SDIN should be acknowledged by CP with a 200 OK. The CP should then send '487 Request Terminated' which will be acknowledged with an ACK from SDIN. Verify that the call gets cancelled and can be traced by looking into the trace from SBC.
SDIN_IOT_CPBIBO_TC04 | N | Yes | Cancel | Test Description CANCEL A call is made from CP to SDIN and the call is cancelled by CP before the call is answered by SDIN. Verify if SDIN is sending 487 "request terminated" on the reception of CANCEL by CP. Execute this test case with preferred codec of the CP. +441583427245 - SDIN test line | The CANCEL method sent by the CP should be acknowledged by BT with a 200 OK. BT should then send '487 Request Terminated' which will be acknowledged with an ACK from CP. Verify that the call gets cancelled and can be traced by looking into the trace from SBC.
SDIN_IOT_CPBIBO_TC05 | N | Yes | Codec | Test Description - Unsupported codec The codec needs to be set to an unsupported codec on the SDIN side. A call is then made from SDIN to CP. Check that the 488 Not Acceptable Here SIP error is sent back from the CP. Check that the full list of codecs is offered to the CP. Check if call is successfully established with good voice quality. Check the packet size used by the codec in both directions. CP/ or tester to dial 01162687112 it will ask CP to enter the number they wish the AMR only call be generated toward, the CP should use the keypad to enter the number they wish to be dialled and then hang up, they will then receive a call within 5 minutes on the number entered with AMR only. This call will be generated from the source number 01162687104. If the CP is supporting AMR generate a call from Soft phone with another codec like G729. Note some HD codecs like G722 are not transcoded on IPEX but a test can be run with this in the offer to ensure the CP releases the call with a 488. | Verify that the 488 Not Acceptable Here error is sent from the CP. Check to ensure that the C3/G9 gets involved by sending a full list of codecs. Make a note of which codec is negotiated Capture the media traces on the SBC. Analyse the rtp stream to ensure there is no asymmetric packetisation. Also ensure that there are no vbd packets which are usually 2 byte packets. Verify that the packetisation rate is as per the CRF. Packetisation rate can be calculated using the payload size in the rtp packet. The call must be successfully established with two way speech and good voice quality. If there is asymmetric packetisation rate the customer must be made aware of the same and asked to rectify the issue. If the CP supports all codecs that IPEX can transcode then you can de-scope this test.
SDIN_IOT_CPBIBO_TC06 | N | Yes | Announcements | Test Description - Early media CP to call +44800 032 4420, Call will result in 183 with SDP and 180 with SDP from C3. CP should be able to hear the announcement, ensure CP confirms they heard the full annoucment clearly, they should state on the test that they can hear it so we can verify an RTP stream is set up. | CP is able to hear the inband announcement properly. Ask CP to confirm on the call that they hear the annoucment.
SDIN_IOT_CPBIBO_TC07 | N | Yes | Refresh | Test Description Session Refresh- A call is made from a CP number to SDIN ensuring that the call is at least 30 minutes long so as to check for session refresh (re-invite/UPDATE) from CP. CP will dial SDIN number +441162687106, it will play music for 30 minutes. Ask CP to terminate the call. | Verify the "timer" and "refresher" values negotiated. Check for session timers and verify if the session is getting refreshed as expected from the refresher using re-invite or update message. Verify that the call gets disconnected successfully after it is terminated by the CP. If the CP does not support session timers and has confirmed this please make note in comments section but still test a long duration call.
SDIN_IOT_CPBIBO_TC08 | N | Yes | Refresh | Test Description - Session Refresh - A call is made from an SDIN number to a CP number. Check for session refresh (re-invite/UPDATE) from CP (during a 30 minute call). CP to dial +441162687108, the IVR will ask the CP to enter the number they wish the long duration call be made to, once the CP enters the destination number on the keypad they should hang up. They will then receive a call back on the hour, this test runs once an hour. Music will be played for 30 minutes and the call will be hung up at 31 minutes. This call will be generated by the source number 01162687104. You can run this test manually using the SNOM. | Verify the "timer" and "refresher" values negotiated, and at what time during the call they occur. Ensure that the CP sends "required:timer" if they send "refresher" parameter as UAC. Check for session timer value and verify if the session is getting refreshed as expected from the refresher using re-invite or update message. Verify that the call gets disconnected by BT. The above verification steps can be found from the call traces. If the CP does not support session timers and has confirmed this please make note in comments section but still test a long duration call.
SDIN_IOT_CPBIBO_TC09 | Y | Yes | DTMF | Test Description DTMF tones as per RFC2833. A call is made from CP to SDIN. CP is expected to send DTMF tones once call is established. The CP's user is expected to generate the tones in sequential order for the IOT test engineer to verify the pattern and accurate delivery of the digits entered. Check if the RTP events are present for each digit entered. CP to dial +441162687101 , the IVR will ask the CP to input DTMF , CP should enter one DTMF digit at a time to hear the IVR detect and repeat back the tone entered. | Verify that 101 telephone event is present in the SDP of INVITE and 200 OK. The DTMF tones should be detected by the IVR. Verify with the media capture that RFC2833 is sent by the CP.
SDIN_IOT_CPBIBO_TC10 | Y | Yes | DTMF | Test Description - DTMF tones as per Inband signalling A call is made from CP to SDIN. CP set to/ should offer RFC2833 and the SDIN endpoint set to Inband. CP is expected to send DTMF tones once call is established. The CP's user is expected to generate the tones in sequential order for the IOT test engineer to verify the pattern and accurate delivery of the digits entered. Ensure the CP use in-band DTMF. Use the preferred codec of CP for this call. CP to dial +441162687107, CP should enter one DTMF digit at a time to hear the IVR detect and repeat back the tone entered. | The DTMF should be detected by the IVR. Verify that 101 telephone event is NOT present in the 200OK and that Inband has been negotiated. Obtain PCAP with RTP to check you can hear the in-band tones from the CP.
SDIN_IOT_CPBIBO_TC11 | Y | Yes | DTMF | Test Description - CP to PSTN - DTMF tones as per Inband signalling. Tones to be generated & verified at both ends. A call is made from CP to PSTN. CP will need to offer in-band only and remove any Telephone events from their INVITE. CP is expected to send DTMF tones once call is established. The user at CP is expected to generate the tones in sequential order in order for the test engineer to verify the pattern and accurate delivery of the digits entered. DTMF tones are then generated from PSTN on the same call and CP needs to verify its accurate delivery. Check if the user at both ends can hear the DTMF tones. Use the preferred codec of CP for this call. +442076201687 – PSTN line | The DTMF tones should be heard by each party. Verify the call is going to C3 and C3 connects the call to PSTN. Verify that 101 telephone event is NOT present in the SDP of INVITE and 200OK. If the CP always offers RFC2833/ Telephone events and cannot remove it from their offer this test can be de-scoped. Make note of this is comment section.
SDIN_IOT_CPBIBO_TC12 | Y | Yes | DTMF | Test Description - DTMF tones as per Inband signalling A call is made from SDIN to CP. Ensure SDIN test phone is set up to only offer in-band. SDIN is expected to send DTMF tones once call is established. The user at SDIN is expected to generate the tones in sequential order in order to verify the pattern and accurate delivery of the digits entered. DTMF tones are then generated from CP side on the same call and SDIN needs to verify its accurate delivery. Check if the user at both ends can hear the DTMF tones. Use the preferred codec of CP for this call. | The DTMF tones should be heard by each party. Verify that 101 telephone event is NOT present in the SDP of INVITE and 200OK.
SDIN_IOT_CPBIBO_TC13 | N | Yes | Hold | Test Description - Call hold by CP. A call is made from CP to SDIN Once the call is successfully established, it is put on hold by the CP. The call needs to be placed on hold for more than 180 seconds. Option A:- Call on hold with media attribute in SDP set to sendonly. When the CP initiates a hold, a re-INVITE is expected with directionality attribute set to sendonly in SDP. SDIN is expected to respond with a recvonly 200 OK. CP is expected to send media packets (RTP/RTCP) during the period of the hold. Option B:- Call on hold with music on hold. When CP initiates a hold, CP plays music on hold. No extra signalling messages are expected during this scenario. Once the call is put on hold for 180 secs, resume the call. Note : If the CP sends C=0.0.0.0 as per RFC 3261 then we need to observe the behaviour of loss of RTP. 1. Check message flow. 2. Check how call hold is handled (using re-INVITE or MOH); if using re-INVITE check in SDP how the hold is being handled. CP should take the call off-hold after 180 secs. CP to dial +441583427245 | This can be verified by looking into the call traces. Verify the RTP stream behaviour during the hold scenario. Verify the call is resumed appropriately with two way speech path.
SDIN_IOT_CPBIBO_TC14 | N | Yes | Hold | Test Description - call hold by BT. A call is made from a CP number to a SDIN number and the call is placed on hold by SDIN. The call needs to be placed on hold for more that 500 seconds. When the call is placed on hold by SDIN; SDIN sends a re-INVITE with media attribute set to sendonly. CP is expected to respond with a recvonly or inactive in the 200 OK. The media packets are expected to flow from SDIN to CP. Once the call is put on hold for 550 secs, resume the call. Check message flow. Check how the end CP responds to the hold initiated by IPEX. SDIN should take the call off-hold after 550 secs. CP to dial 01162687110 , it will put the CP on hold for 550 seconds and play MOH, it will then take them off hold and shortly after terminate the call. | Verify the call is resumed appropriately with two way speech path between SDIN and CP. If the call drops after 180 secs this test can be passed but a note should be made to reflect this in the comments field. Make note of CP's responses to RE-INVITE's.
SDIN_IOT_CPBIBO_TC15 | N | Yes | Short code | Short code test call - CP to dial speaking clock by dialling 123, this is to verify the CP sends short codes in the correct format. SIP URI = <sip:123;phone-context=+44@uk.sdin.bt.net;user=phone> | CP's Request URI and TO header should look as follows: SIP URI = <sip:123;phone-context=+44@uk.sdin.bt.net;user=phone> CP must not send +44123. CP should hear the speaking clock. Ensure CP sends the "user=phone" and "phone-context=+44".
SDIN_IOT_CPBIBO_TC16 | N | Yes | Emergency | Test Description - Emergency Call without ii digits A call is made from CP to 999 and the CP does not add ii digits. Verify message formats as per expected results. As these calls will go to live 999 operators 2 days notice is required Note Ask CP to call 101, 105, 111, 112 and 119 as well and verify the message format. | Check that Request URI only carries 999 instead of +44999 for this call. Check if call is routed to PSTN and check if CLI is delivered and II digits are correctly appended by S3 end-point (999ii). Check if call is successful. The INVITE sent by the CP-UT is expected to have the headers in the following format Request URI: sip:999;phone-context=+44@109.159.136.170:5060;user=phone To: <sip:999;phone-context=+44@109.159.136.170;user=phone>> Note number should not have +44 appended to it and the CP must send "phone-context=+44" From: "xyz" <sip:+445600570031@ <Customer Domain > Note number should be in international format. Note, the numbers used here are for illustration purpose only and if CP-UT is IP Based customer then CP-UT will send IP address instead of domain name.
SDIN_IOT_CPBIBO_TC17 | N | Yes | Emergency | Test Description - Emergency call with ii digits A call is made from CP to 999 number and the CP can send ii digits. Check that Request URI only carries 999ii instead of +44xxx for this call using call traces. Check if call is routed to C3 Check if CLI is delivered and ii digits are correctly appended by CP. Check if call is successful. As these calls will go to live 999 operators 2 days notice is required Note Ask CP to call 101, 105, 111, 112 and 119 as well and verify the message format. | Check that Request URI only carries 999ii (egg: 99970020) instead of +44999 for this call using traces. Check if call is routed to PSTN. Check if CLI is delivered and II digits are correctly appended by CP itself. Check if call is successful. The INVITE sent by the CP is expected to have the headers in the following format Request URI: sip:999ii;phone-context=+44@109.159.136.170:5060;user=phone To: <sip:999ii;phone-context=+44@109.159.136.170;user=phone>> Note number should not have +44 appended to it and the CP must send "phone-context=+44" From: "xyz" <sip:+445600570031@ <Customer Domain > Note the numbers used here are for illustration purpose only.
SDIN_IOT_CPBIBO_TC18 | N | Yes | Emergency | Test Description - Emergency Call from CP to 112. CP to add their ii digits. Check if call is routed to C3. Check if CLI is delivered and ii digits are correctly appended by S3 end-point. Check if call is successful. Check that Request URI only carries 112 instead of +44112 for this call. | Check the Request URI only carries 112 instead of +44112 for this call. This can be verified by looking at the call traces. Verify that the call get connected successfully to the PSTN site and cleared successfully by looking into the trace. Check if call is routed to PSTN. Check if call is successful. The INVITE sent by the CP is expected to have the headers in the following format Request URI: sip:112;phone-context=+44@109.159.136.170:5060;user=phone To: <sip:112;phone-context=+44@109.159.136.170;user=phone>> Note number should not have +44 appended to it and the CP must send "phone-context=+44" From: "xyz" <sip:+445600570031@ <Customer Domain > Note number should be in international format Note the numbers used here are for illustration purpose only
SDIN_IOT_CPBIBO_TC19 | N | Yes | SDP | Test Description - NO SDP, SDIN to CP with no SDP in the INVITE Does the CP's equipment supports receiving an Invite with no SDP/ delayed offer? Place an audio call from SDIN to CP call with no SDP in Invite. To generate this test the CP dials +441162687105, once connected to the IVR you will be prompted to enter the number in which you want the delayed offer test call to be generated toward, once entered on the keypad hang up. The number entered will then receive a delayed offer call at 5, 10 or 15 minutes past the hour. | Verify that SDIN's INVITE has no SDP. Ensure that the response from CP side contains all the codecs enabled. Check the codec that SDIN then chooses for the call. Verify the call is successful with no issues with voice quality. Verify how PRACK behaves when negotiated.
SDIN_IOT_CPBIBO_TC20 | N | Yes | SDP | Test Description - NO SDP, CP to SDIN with no SDP in the INVITE CP to confirm is they support sending an Invite with no SDP. Place an audio call from CP to SDIN call with no SDP in Invite. CP to dial +441162687113, CP should send a delayed offer/ INVITE no SDP. | Verify that the CP's INVITE has no SDP. Ensure that the response from BT side contains all the codecs enabled. Check the codec the CP then chooses for the call. Verify the call is successful with no issues with voice quality.
SDIN_IOT_CPBIBO_TC21 | N | Yes | 503 | 500 Internal Sever Error CP to SDIN, CP to dial +441162687102. Call should be released with a 503. | CP should receive a 500, ensure call terminates.
SDIN_IOT_CPBIBO_TC22 | N | Yes | 404 | 404 Not Found CP to SDIN,CP to dial +441162687103. Call should be released with a 404 | Ensure the CP does not re-attempt on the receipt of a 404 not found. Ensure the call is terminated on receipt of a 404.
SDIN_IOT_CPBIBO_TC23 | N | Yes | 486 | 486 Busy Here CP to SDIN, CP to dial +441162687104 | Ensure the CP does not re-attempt on the receipt of a 486. Ensure the call is terminated on the receipt of a 486.
SDIN_IOT_CPBIBO_TC24 | N | Yes | 403 | 403 Forbidden CP to SDIN, CP to dial 01162687109 | Ensure the CP does not re-attempt on the receipt of a 403. Ensure the call is terminated on the receipt of a 403.
SDIN_IOT_CPBIBO_TC25 | N | Yes | Anonymous | Anonymous test CP to SDIN, CP to dial ++441583427245 and anonymise their from CLI. SDIN to CP, anonymise the from CLI and ensure CP does not display the PAID. | Ensure the CP still sends a PAID. Check the format of the INVITE.